## Bank_Mandates_Project_Gantt
Task | Description | Start | End | Phase | Progress | Version
Data collection & wrangling | Gather mandate data from all banks, clean and unify formats, and prepare for processing. | 2025-07-07 | 2025-08-08 | Phase 1 | 50% | 1
Role logic definition | Define rules for categorizing signers into primary, secondary, and others. | 2025-07-07 | 2025-07-10 | Phase 1 | 100% | 1
Dashboard & Mandates UI Build | Develop the full stack (Backend and front-end view) for the dashboard and mandates page using Python, HTML/CSS/JS. | 2025-07-15 | 2025-08-05 | Phase 1 | 100% | 1
Stakeholder feedback & iteration | Review feedback from Toan and others, make improvements to the dashboard and logic. | 2025-07-15 | 2025-08-04 | Phase 1 | 100% | 1
Finalize Phase 1 | Wrap up and validate all Phase 1 deliverables before internship ends. | 2025-08-04 | 2025-08-08 | Phase 1 | 40% | 1
End of Internship | Completion of internship period. | 2025-08-22 | 2025-08-22 | Phase 1 | 0% | 1
Data Dictionary Integration | Get Data Dictionary for all mandates data from each of the banks in the scope. Integrate data dictionary for standardized field mappings across banks. | 2025-09-29 | 2025-10-03 | Phase 2 | 0% | 1
Begin Signers/Update/Role Based Access Modules | Start development of signer management and update functionality modules. | 2025-09-29 | 2025-11-28 | Phase 2 | 0% | 1
Testing & QA | Comprehensive testing of all modules and functionality. | 2025-12-08 | 2025-12-12 | Phase 3 | 0% | 1
User Training & Documentation | Create user guides and conduct training sessions for end users. | 2025-12-15 | 2025-12-19 | Phase 3 | 0% | 1
Final Deployment | Deploy the completed system to production environment. | 2025-12-22 | 2025-12-31 | Phase 3 | 0% | 1
Post-Deployment Support | Monitor system performance and provide initial support. | 2026-01-05 | 2026-01-23 | Phase 3 | 0% | 1
Begin Mail Automation/ Agent Modules | Start development of mail automation and AI Agent to populate forms/ letters | 2026-01-05 | 2026-02-27 | Phase 1 | 0% | 2
Email Automation Setup | Configure automated email notifications for mandate updates and alerts. | 2026-02-02 | 2026-02-27 | Phase 1 | 0% | 2
Testing & QA | Comprehensive testing of all modules and functionality. | 2026-03-02 | 2026-03-06 | Phase 2 | 0% | 2
User Training & Documentation | Create user guides and conduct training sessions for end users. | 2026-03-09 | 2026-03-13 | Phase 2 | 0% | 2
Final Deployment | Deploy the completed system to production environment. | 2026-03-17 | 2026-03-31 | Phase 2 | 0% | 2
Post-Deployment Support | Monitor system performance and provide initial support. | 2026-04-06 | 2026-04-17 | Phase 2 | 0% | 2
Project Closure | Final documentation and project handover. | 2026-04-20 | 2026-04-30 | Phase 2 | 0% | 2